## Sheet1
Feature	Category	Priority	Status	Complexity	Dependencies	Notes/Details	Due Date
Define and test Span and Position types	Core Language	Critical	Completed	Low	None		07/22/25
Create AST Node Structure	Core Language	Critical	Planning	Medium	None		07/25/25
Define basic syntax/grammar	Core Language	Critical	Planning	Low	None	Some of this is demonstrated in the example files, but a proper grammar is probably necessary.	07/28/25
Build basic Lexer to parse source code	Core Language	Critical	In Progress	Medium	None		08/01/25
Implement basic parser	Core Language	Critical	Planning	Medium	Lexer to produce Tokens, Basic AST defined	Implement basic expression parsing and statement parsing. This doesn’t include control flow, classes, or functions.	08/05/25
Span-based error handling	Diagnostics	High	Completed	Medium	Basic AST	Replace Position with Span for better error ranges. Finish implementation of the ErrorHandler class.
Variable Declarations	Core Language	Critical	Planning	Low	Basic Parser, AST
Function Declarations	Core Language	Critical	Planning	High	Variable Declarations, Parser, Lexer
Control Flow	Core Language	Critical	Planning	Medium	Lexer, Basic Parser
Define primitive types	Type System	Critical	Planning	Medium	Grammar
Basic Type Checking Infrastructure	Type System	Critical	Planning	High	AST, Parser, Lexer, Grammar, primitive types
Type Annotation Syntax	Type System	Critical	Planning	Medium	None
Variable Binding/Lookup	Type System	Critical	Planning	Medium	Parser with variable declarations.
Add REPL	Tooling	Medium	Idea	Low	Minimal compiler	This should be added after we’re able to JIT compile single lines in LLVM
Basic CodeGen	Core Language	Critical	Planning	High	Working type checker, parser, and lexer.	This should use the Strategy pattern to have different codegen strategies. We probably want a Factory that generates a JIT Compiler strategy and a BuildNative strategy.