## Sheet1
Feature	Category	Priority	Status	Complexity	Dependencies	Notes/Details	Due Date
Build basic Lexer to parse source code	Core Language	Critical	In Progress	Medium	None		08/01/25
Define basic syntax/grammar	Core Language	Critical	Planning	Low	None	Some of this is demonstrated in the example files, but a proper grammar is probably necessary.	07/28/25
Span-based error handling	Diagnostics	High	Idea	Medium	Basic AST	Replace Position with Span for better error ranges. Finish implementation of the ErrorHandler class.
Implement basic parser	Core Language	Critical	Planning	Medium	Lexer to produce Tokens, Basic AST defined	Implement basic expression parsing and statement parsing. This doesn’t include control flow, classes, or functions.	08/05/25
Create AST Node Structure	Core Language	Critical	Planning	Medium	None		07/25/25
Variable Declarations	Core Language	Critical	Planning	Low	Basic Parser, AST
Function Declarations	Core Language	Critical	Planning	High	Variable Declarations, Parser, Lexer
Control Flow	Core Language	Critical	Planning	Medium	Lexer, Basic Parser
Define primitive types	Type System	Critical	Planning	Medium	Grammar
Basic Type Checking Infrastructure	Type System	Critical	Planning	High	AST, Parser, Lexer, Grammar, primitive types
Type Annotation Syntax	Type System	Critical	Planning	Medium	None
Variable Binding/Lookup	Type System	Critical	Planning	Medium	Parser with variable declarations.